## INDEX (hidden)
Order Placed
Order Approved
PO Created
PO Sent to Vendor
Order Confirmed
In Production
Ready for Shipment
In Transit
QC Checks
Delivered to DIAMOND DC
Shipment Complete

## Sheet3 (hidden)
[10 empty] | PO Number | Sum of Qty | Sum of OTB Value in AED
[6 empty] | COUNTRY | Sum of OTB Value in AED | Collection | Sum of OTB Value in AED | (blank)
Order Status | Count of PO Number |  |  |  |  | Bahrain | 389978 | NO COLLECTION | 492143 | PO00056256 | 98 | 20208
CONFIRMED | 27 |  |  |  |  | Oman | 327422 | (blank) |  | PO00056257 | 96 | 16233
HOLD | 30 |  |  |  |  | UAE | 287632 | BLUE_ROSETTE | 175170 | PO00056258 | 177 | 16637
NOT PLACED | 41 |  |  |  |  | (blank) |  | BRILLIANT | 41876 | PO00056259 | 139 | 16881
(blank) | [5 empty] | Qatar | 293119 | PYRAMID | 81001 | PO00056260 | 185 | 24667
Grand Total | 98 |  |  |  |  | Kuwait | 224877 | Floret_21 | 263351 | PO00056261 | 196 | 16051
[6 empty] | Saudi | 308390 | Springs | 20134 | PO00056262 | 142 | 24991
Category | Brand | Sum of Delay in Deliver |  |  |  | Grand Total | 1831418 | ADORE | 24159 | PO00056263 | 185 | 12099
DIAMOND |  | 685 | [5 empty] | CADEAU_SINGLE_CUT_P | 118051 | PO00056264 | 191 | 22079
FASHION |  | 706 | [5 empty] | GLAM | 35018 | PO00056265 | 85 | 20134
GOLD |  | 771 | [5 empty] | ETERNAL | 151777 | PO00056266 | 202 | 24159
(blank) | [7 empty] | GRANADA | 173398 | PO00056267 | 145 | 20440
FINE | Stella Doro | 54 | [5 empty] | PICK_ANY | 72054 | PO00056268 | 103 | 13598
FINE | Alif | 167 | [5 empty] | Amara | 183286 | PO00056269 | 183 | 15318
FINE | Revolve Men | 101 | [5 empty] | Grand Total | 1831418 | PO00056270 | 121 | 12137
Grand Total |  | 2484 | [7 empty] | PO00056271 | 141 | 22311
[10 empty] | PO00056272 | 195 | 20118
[10 empty] | PO00056273 | 169 | 17991
[10 empty] | PO00056274 | 208 | 17666
[10 empty] | PO00056275 | 210 | 21234
[10 empty] | PO00056276 | 188 | 14436
[10 empty] | PO00056277 | 169 | 13459
[10 empty] | PO00056278 | 201 | 20441
[10 empty] | PO00056279 | 162 | 24509
[10 empty] | PO00056280 | 202 | 21263
[10 empty] | PO00056281 | 101 | 17630
[10 empty] | PO00056282 | 190 | 14101
[10 empty] | PO00056283 | 160 | 22363
[10 empty] | PO00056284 | 128 | 19315
[10 empty] | PO00056285 | 186 | 20482
Order Status | Brand | Collection | Sum of Qty | [6 empty] | PO00056286 | 189 | 12165
CONFIRMED | GAIA | BRILLIANT | 223 | [6 empty] | PO00056287 | 96 | 23689
CONFIRMED | One Six Eight | Amara | 301 | [6 empty] | PO00056288 | 174 | 20031
CONFIRMED | Springs | BLUE_ROSETTE | 403 | [6 empty] | PO00056289 | 187 | 24096
CONFIRMED | Springs | Springs | 85 | [6 empty] | PO00056290 | 161 | 14580
CONFIRMED | Nakshatrah | NO COLLECTION | 463 | [6 empty] | PO00056291 | 161 | 17475
CONFIRMED | Pyramid | PYRAMID | 543 | [6 empty] | PO00056292 | 206 | 20238
CONFIRMED | Anmol 21K | Floret_21 | 876 | [6 empty] | PO00056293 | 202 | 20279
CONFIRMED | KIKU | CADEAU_SINGLE_CUT_P | 137 | [6 empty] | PO00056294 | 144 | 14552
CONFIRMED | Alif | ETERNAL | 393 | [6 empty] | PO00056295 | 149 | 13984
CONFIRMED | OGL | GRANADA | 286 | [6 empty] | PO00056296 | 104 | 17077
CONFIRMED | Revolve Men | NO COLLECTION | 151 | [6 empty] | PO00056297 | 139 | 22851
CONFIRMED | Illusion Round | Amara | 94 | [6 empty] | PO00056298 | 160 | 23602
HOLD | GAIA | BRILLIANT | 177 | [6 empty] | PO00056299 | 142 | 24007
HOLD | One Six Eight | Amara | 106 | [6 empty] | PO00056300 | 140 | 16566
HOLD | Springs | BLUE_ROSETTE | 789 | [6 empty] | PO00056301 | 128 | 24558
HOLD | Stella Doro | NO COLLECTION | 491 | [6 empty] | PO00056302 | 183 | 12019
HOLD | Nakshatrah | NO COLLECTION | 687 | [6 empty] | PO00056303 | 137 | 22376
HOLD | Anmol 21K | Floret_21 | 126 | [6 empty] | PO00056304 | 185 | 24521
HOLD | Baguette | ADORE | 202 | [6 empty] | PO00056305 | 111 | 18663
HOLD | KIKU | CADEAU_SINGLE_CUT_P | 353 | [6 empty] | PO00056306 | 126 | 15415
HOLD | Diana | GLAM | 336 | [6 empty] | PO00056307 | 157 | 23084
HOLD | Alif | ETERNAL | 469 | [6 empty] | PO00056308 | 183 | 16186
HOLD | OGL | GRANADA | 506 | [6 empty] | PO00056309 | 144 | 21755
HOLD | Youth | PICK_ANY | 189 | [6 empty] | PO00056310 | 153 | 13900
HOLD | Revolve Men | NO COLLECTION | 305 | [6 empty] | PO00056311 | 181 | 18406
NOT PLACED | One Six Eight | Amara | 105 | [6 empty] | PO00056312 | 115 | 14165
NOT PLACED | Springs | BLUE_ROSETTE | 336 | [6 empty] | PO00056313 | 151 | 17508
NOT PLACED | Stella Doro | NO COLLECTION | 153 | [6 empty] | PO00056314 | 126 | 21061
NOT PLACED | Nakshatrah | NO COLLECTION | 1340 | [6 empty] | PO00056315 | 113 | 13463
NOT PLACED | Pyramid | PYRAMID | 183 | [6 empty] | PO00056316 | 153 | 19700
NOT PLACED | Anmol 21K | Floret_21 | 1127 | [6 empty] | PO00056317 | 182 | 19809
NOT PLACED | KIKU | CADEAU_SINGLE_CUT_P | 361 | [6 empty] | PO00056318 | 102 | 13102
NOT PLACED | Alif | ETERNAL | 460 | [6 empty] | PO00056319 | 168 | 13122
NOT PLACED | OGL | GRANADA | 583 | [6 empty] | PO00056320 | 101 | 14017
NOT PLACED | Youth | PICK_ANY | 656 | [6 empty] | PO00056321 | 183 | 21487
NOT PLACED | Revolve Men | NO COLLECTION | 270 | [6 empty] | PO00056322 | 151 | 19165
NOT PLACED | Illusion Round | Amara | 632 | [6 empty] | PO00056323 | 106 | 21294
(blank) | (blank) | (blank) | [7 empty] | PO00056324 | 120 | 20224
Grand Total |  |  | 14897 | [6 empty] | PO00056325 | 119 | 13925
[10 empty] | PO00056326 | 193 | 18047
[10 empty] | PO00056327 | 103 | 20665
[10 empty] | PO00056328 | 142 | 22870
[10 empty] | PO00056329 | 129 | 24746
[10 empty] | PO00056330 | 162 | 21326
[10 empty] | PO00056331 | 105 | 16619
[10 empty] | PO00056332 | 99 | 16962
[10 empty] | PO00056333 | 94 | 14318
[10 empty] | PO00056334 | 94 | 13434
[10 empty] | PO00056335 | 138 | 12143
[10 empty] | PO00056336 | 160 | 12859
[10 empty] | PO00056337 | 95 | 21885
[10 empty] | PO00056338 | 168 | 16029
|  |  |  | Brand | Sum of OTB Value in AED |  |  |  |  | PO00056339 | 160 | 16113
|  |  |  | GAIA | 41876 |  |  |  |  | PO00056340 | 159 | 21310
|  |  |  | One Six Eight | 77880 |  |  |  |  | PO00056341 | 106 | 22800
|  |  |  | Springs | 195304 |  |  |  |  | PO00056342 | 191 | 24002
|  |  |  | (blank) | [5 empty] | PO00056343 | 156 | 19444
|  |  |  | Stella Doro | 79055 |  |  |  |  | PO00056344 | 206 | 15064
|  |  |  | Nakshatrah | 329247 |  |  |  |  | PO00056345 | 106 | 24354
|  |  |  | Pyramid | 81001 |  |  |  |  | PO00056346 | 173 | 19146
|  |  |  | Anmol 21K | 263351 |  |  |  |  | PO00056347 | 103 | 14205
|  |  |  | Baguette | 24159 |  |  |  |  | PO00056348 | 169 | 15697
PO Month | Sum of OTB Value in AED |  |  | KIKU | 118051 |  |  |  |  | PO00056349 | 208 | 20280
January | 70709 |  |  | Diana | 35018 |  |  |  |  | PO00056350 | 115 | 23323
February | 175138 |  |  | Alif | 151777 |  |  |  |  | PO00056351 | 160 | 20389
April | 245634 |  |  | OGL | 173398 |  |  |  |  | PO00056352 | 208 | 22096
May | 298010 |  |  | Youth | 72054 |  |  |  |  | PO00056353 | 205 | 20224
July | 168878 |  |  | Revolve Men | 83841 |  |  |  |  | Grand Total | 14897 | 1831418
September | 24667 |  |  | Illusion Round | 105406
(blank) |  |  |  | Grand Total | 1831418
March | 263104
June | 347515
August | 237763
Grand Total | 1831418
PO Sent to Vendor
Order Confirmed
In Production
Ready for Shipment
In Transit
QC Checks
Delivered to DIAMOND DC
Shipment Complete
Brand | Vendor Name
GAIA | Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
One Six Eight | Golden Star Exports Ltd
LOTUS JEWELS FZC
Springs | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
(blank) | (blank)
Stella Doro | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
Nakshatrah | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
RENAISSANCE JEWELLERY DMCC
Pyramid | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
Anmol 21K | Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
RENAISSANCE JEWELLERY DMCC
Baguette | LOTUS JEWELS FZC
KIKU | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
RENAISSANCE JEWELLERY DMCC
Diana | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
Alif | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
OGL | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
Youth | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
Revolve Men | Golden Star Exports Ltd
LOTUS JEWELS FZC
RENAISSANCE JEWELLERY DMCC
Illusion Round | Golden Star Exports Ltd
Lamar Jewellery FZ-LLC
LOTUS JEWELS FZC
Grand Total
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## Report
PO AND SHIPMENT DETAILS REPORT
Category | Brand Manager | Brand | Collection | PO Number | OTB | OTB DESCRIPTION | OTB Value in AED | Qty | COUNTRY | Vendor Name | Mode of Buying | Order Status | OTB Creation Date | OTB Month | PO Creation Date | PO Month | ETA | Order Placed | Order Approved | PO Created | PO Sent to Vendor | Order Confirmed | In Production | Ready for Shipment | In Transit | QC Checks | Delivered to DIAMOND DC | Shipment Complete | Progress | Status | Order Received Date | Order Received Month | Delay in Deliver
[18 empty] | 🧾 Procurement | ✅ Finance | 📤 Procurement | 📤 Procurement | 🤝 Procurement | 🏭 Procurement | 🚢 Logistics | 🌍 Logistics | 🧪 Quality Control | 📦 Logistics / Pricing | 📊 Pricing / Finance
FINE | Naju | Stella Doro | NO COLLECTION | PO00056256 | 100 | Replenishment | 20208 | 98 | Qatar | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-04-16 | April | 2025-04-25 | April | 2025-06-27 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-07-16 | July | 19
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056257 | 80 | Newness | 16233 | 96 | Kuwait | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-06-22 | June | 2025-07-01 | July | 2025-09-02 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-09-27 | September | 25
DIAMOND | Neha | GAIA | BRILLIANT | PO00056258 | 42 | Replenishment | 16637 | 177 | Bahrain | Lamar Jewellery FZ-LLC | CONSIGNMENT | HOLD | 2025-04-21 | April | 2025-04-30 | April | 2025-07-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-07-15 | July | 13
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056259 | 72 | Replenishment | 16881 | 139 | Qatar | RENAISSANCE JEWELLERY DMCC | DIRECT | CONFIRMED | 2025-02-14 | February | 2025-02-25 | February | 2025-04-29 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-05-05 | May | 6
FINE | Naju | Stella Doro | NO COLLECTION | PO00056260 | 73 | Newness | 24667 | 185 | Bahrain | Golden Star Exports Ltd | DIRECT | HOLD | 2025-08-24 | August | 2025-09-02 | September | 2025-11-04 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-11-10 | November | 6
DIAMOND | Tanvir | Pyramid | PYRAMID | PO00056261 | 100 | Newness | 16051 | 196 | Kuwait | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-05-10 | May | 2025-05-20 | May | 2025-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-08-25 | August | 34
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056262 | 34 | Replenishment | 24991 | 142 | Saudi | Lamar Jewellery FZ-LLC | DIRECT | CONFIRMED | 2025-04-25 | April | 2025-05-06 | May | 2025-07-08 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-08-25 | August | 48
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056263 | 66 | Newness | 12099 | 185 | Qatar | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-05-11 | May | 2025-05-20 | May | 2025-07-22 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-08-26 | August | 35
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056264 | 100 | Replenishment | 22079 | 191 | Oman | Lamar Jewellery FZ-LLC | DIRECT | CONFIRMED | 2025-01-12 | January | 2025-01-21 | January | 2025-03-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-05-01 | May | 37
FASHION | Nigora | Springs | Springs | PO00056265 | 54 | Newness | 20134 | 85 | Bahrain | Golden Star Exports Ltd | DIRECT | CONFIRMED | 2025-04-16 | April | 2025-04-25 | April | 2025-06-27 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-07-21 | July | 24
DIAMOND | Harry | Baguette | ADORE | PO00056266 | 74 | Newness | 24159 | 202 | Qatar | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-05-01 | May | 2025-05-12 | May | 2025-07-14 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-08-31 | August | 48
FASHION | Nigora | KIKU | CADEAU_SINGLE_CUT_P | PO00056267 | 46 | Newness | 20440 | 145 | UAE | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-04-27 | April | 2025-05-06 | May | 2025-07-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-08-18 | August | 41
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056268 | 40 | Newness | 13598 | 103 | Bahrain | Golden Star Exports Ltd | DIRECT | HOLD | 2025-05-02 | May | 2025-05-13 | May | 2025-07-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-08-12 | August | 28
DIAMOND | Tanvir | Diana | GLAM | PO00056269 | 80 | Replenishment | 15318 | 183 | Kuwait | Golden Star Exports Ltd | DIRECT | HOLD | 2025-03-02 | March | 2025-03-11 | March | 2025-05-13 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-05-24 | May | 11
DIAMOND | Neha | GAIA | BRILLIANT | PO00056270 | 31 | Newness | 12137 | 121 | Oman | Lamar Jewellery FZ-LLC | CONSIGNMENT | CONFIRMED | 2025-05-28 | May | 2025-06-06 | June | 2025-08-08 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-09-15 | September | 38
FINE | Naju | Alif | ETERNAL | PO00056271 | 59 | Newness | 22311 | 141 | Saudi | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-02-09 | February | 2025-02-18 | February | 2025-04-22 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-05-01 | May | 9
FASHION | Nigora | OGL | GRANADA | PO00056272 | 32 | Replenishment | 20118 | 195 | Oman | Golden Star Exports Ltd | DIRECT | HOLD | 2025-06-09 | June | 2025-06-18 | June | 2025-08-20 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-09-23 | September | 34
FASHION | Nigora | OGL | GRANADA | PO00056273 | 39 | Newness | 17991 | 169 | UAE | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-03-28 | March | 2025-04-08 | April | 2025-06-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-06-16 | June | 6
FASHION | Nigora | KIKU | CADEAU_SINGLE_CUT_P | PO00056274 | 57 | Replenishment | 17666 | 208 | Bahrain | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-04-26 | April | 2025-05-06 | May | 2025-07-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-08-25 | August | 48
FINE | Naju | Alif | ETERNAL | PO00056275 | 263 | Newness | 21234 | 210 | UAE | Golden Star Exports Ltd | DIRECT | CONFIRMED | 2025-04-19 | April | 2025-04-29 | April | 2025-07-01 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-08-19 | August | 49
DIAMOND | Tanvir | Youth | PICK_ANY | PO00056276 | 37 | Newness | 14436 | 188 | Qatar | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-06-30 | June | 2025-07-09 | July | 2025-09-10 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-09-29 | September | 19
FINE | Naju | Revolve Men | NO COLLECTION | PO00056277 | 67 | Replenishment | 13459 | 169 | UAE | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-04-28 | April | 2025-05-07 | May | 2025-07-09 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-07-28 | July | 19
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056278 | 63 | Newness | 20441 | 201 | Saudi | Lamar Jewellery FZ-LLC | DIRECT | CONFIRMED | 2025-06-08 | June | 2025-06-17 | June | 2025-08-19 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-10-02 | October | 44
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056279 | 75 | Replenishment | 24509 | 162 | Saudi | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-03-19 | March | 2025-03-28 | March | 2025-05-30 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-06-22 | June | 23
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056280 | 55 | Replenishment | 21263 | 202 | Oman | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-06-09 | June | 2025-06-18 | June | 2025-08-20 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-09-03 | September | 14
FASHION | Nigora | OGL | GRANADA | PO00056281 | 72 | Replenishment | 17630 | 101 | UAE | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-05-14 | May | 2025-05-23 | May | 2025-07-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-07-30 | July | 5
FASHION | Nigora | OGL | GRANADA | PO00056282 | 77 | Replenishment | 14101 | 190 | Oman | Lamar Jewellery FZ-LLC | DIRECT | CONFIRMED | 2025-03-08 | March | 2025-03-18 | March | 2025-05-20 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-06-07 | June | 18
FINE | Naju | Alif | ETERNAL | PO00056283 | 35 | Replenishment | 22363 | 160 | Oman | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-07-24 | July | 2025-08-04 | August | 2025-10-06 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-10-20 | October | 14
DIAMOND | Harry | One Six Eight | Amara | PO00056284 | 110 | Newness | 19315 | 128 | Oman | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-02-02 | February | 2025-02-11 | February | 2025-04-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-05-14 | May | 29
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056285 | 38 | Replenishment | 20482 | 186 | Oman | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-03-19 | March | 2025-03-28 | March | 2025-05-30 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-06-25 | June | 26
DIAMOND | Tanvir | Youth | PICK_ANY | PO00056286 | 64 | Newness | 12165 | 189 | Oman | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-01-22 | January | 2025-01-31 | January | 2025-04-04 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-04-13 | April | 9
FASHION | Nigora | OGL | GRANADA | PO00056287 | 49 | Newness | 23689 | 96 | Oman | Golden Star Exports Ltd | DIRECT | CONFIRMED | 2025-04-25 | April | 2025-05-06 | May | 2025-07-08 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-08-23 | August | 46
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056288 | 68 | Newness | 20031 | 174 | UAE | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-03-02 | March | 2025-03-11 | March | 2025-05-13 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-05-20 | May | 7
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056289 | 73 | Replenishment | 24096 | 187 | Qatar | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-06-17 | June | 2025-06-26 | June | 2025-08-28 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-10-05 | October | 38
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056290 | 42 | Replenishment | 14580 | 161 | Oman | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-07-10 | July | 2025-07-21 | July | 2025-09-22 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-10-13 | October | 21
FASHION | Nigora | OGL | GRANADA | PO00056291 | 100 | Replenishment | 17475 | 161 | Qatar | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-02-08 | February | 2025-02-18 | February | 2025-04-22 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-04-29 | April | 7
FINE | Naju | Revolve Men | NO COLLECTION | PO00056292 | 48 | Replenishment | 20238 | 206 | Qatar | Golden Star Exports Ltd | DIRECT | HOLD | 2025-04-14 | April | 2025-04-23 | April | 2025-06-25 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-08-01 | August | 37
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056293 | 62 | Newness | 20279 | 202 | Oman | RENAISSANCE JEWELLERY DMCC | DIRECT | NOT PLACED | 2025-01-18 | January | 2025-01-28 | January | 2025-04-01 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-04-28 | April | 27
FASHION | Nigora | KIKU | CADEAU_SINGLE_CUT_P | PO00056294 | 64 | Newness | 14552 | 144 | Oman | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-04-24 | April | 2025-05-05 | May | 2025-07-07 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-07-22 | July | 15
FINE | Naju | Alif | ETERNAL | PO00056295 | 70 | Newness | 13984 | 149 | Oman | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-03-23 | March | 2025-04-01 | April | 2025-06-03 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-06-18 | June | 15
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056296 | 45 | Newness | 17077 | 104 | UAE | Golden Star Exports Ltd | DIRECT | HOLD | 2025-06-29 | June | 2025-07-08 | July | 2025-09-09 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-10-03 | October | 24
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056297 | 56 | Newness | 22851 | 139 | Saudi | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-03-27 | March | 2025-04-07 | April | 2025-06-09 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-07-16 | July | 37
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056298 | 42 | Replenishment | 23602 | 160 | Bahrain | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-06-08 | June | 2025-06-17 | June | 2025-08-19 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-09-14 | September | 26
FASHION | Nigora | OGL | GRANADA | PO00056299 | 64 | Newness | 24007 | 142 | UAE | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-08-05 | August | 2025-08-14 | August | 2025-10-16 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-11-03 | November | 18
DIAMOND | Tanvir | Pyramid | PYRAMID | PO00056300 | 63 | Newness | 16566 | 140 | Saudi | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-06-24 | June | 2025-07-03 | July | 2025-09-04 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-09-26 | September | 22
DIAMOND | Harry | Illusion Round | Amara | PO00056301 | 39 | Replenishment | 24558 | 128 | Bahrain | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-05-26 | May | 2025-06-04 | June | 2025-08-06 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-09-01 | September | 26
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056302 | 57 | Newness | 12019 | 183 | Bahrain | Golden Star Exports Ltd | DIRECT | HOLD | 2025-04-15 | April | 2025-04-24 | April | 2025-06-26 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-07-04 | July | 8
FASHION | Nigora | KIKU | CADEAU_SINGLE_CUT_P | PO00056303 | 61 | Replenishment | 22376 | 137 | Bahrain | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-06-21 | June | 2025-07-01 | July | 2025-09-02 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-10-19 | October | 47
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056304 | 75 | Replenishment | 24521 | 185 | Oman | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-06-11 | June | 2025-06-20 | June | 2025-08-22 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-10-11 | October | 50
FASHION | Nigora | KIKU | CADEAU_SINGLE_CUT_P | PO00056305 | 38 | Replenishment | 18663 | 111 | Saudi | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-06-05 | June | 2025-06-16 | June | 2025-08-18 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-10-02 | October | 45
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056306 | 63 | Replenishment | 15415 | 126 | Saudi | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-08-09 | August | 2025-08-19 | August | 2025-10-21 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-11-02 | November | 12
DIAMOND | Harry | Illusion Round | Amara | PO00056307 | 67 | Newness | 23084 | 157 | UAE | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-02-22 | February | 2025-03-04 | March | 2025-05-06 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-06-04 | June | 29
FINE | Naju | Alif | ETERNAL | PO00056308 | 59 | Replenishment | 16186 | 183 | Qatar | Golden Star Exports Ltd | DIRECT | CONFIRMED | 2025-01-11 | January | 2025-01-21 | January | 2025-03-25 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-04-11 | April | 17
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056309 | 39 | Replenishment | 21755 | 144 | Kuwait | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-08-18 | August | 2025-08-27 | August | 2025-10-29 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-11-26 | November | 28
FINE | Naju | Stella Doro | NO COLLECTION | PO00056310 | 49 | Newness | 13900 | 153 | Bahrain | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-06-04 | June | 2025-06-13 | June | 2025-08-15 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-08-23 | August | 8
DIAMOND | Tanvir | Youth | PICK_ANY | PO00056311 | 60 | Replenishment | 18406 | 181 | Qatar | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-02-19 | February | 2025-02-28 | February | 2025-05-02 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-05-28 | May | 26
FINE | Naju | Alif | ETERNAL | PO00056312 | 77 | Replenishment | 14165 | 115 | Kuwait | Golden Star Exports Ltd | DIRECT | HOLD | 2025-03-30 | March | 2025-04-08 | April | 2025-06-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-07-07 | July | 27
FASHION | Nigora | Springs | BLUE_ROSETTE | PO00056313 | 44 | Newness | 17508 | 151 | Qatar | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-05-20 | May | 2025-05-29 | May | 2025-07-31 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-08-27 | August | 27
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056314 | 54 | Replenishment | 21061 | 126 | Kuwait | Golden Star Exports Ltd | DIRECT | HOLD | 2025-05-04 | May | 2025-05-13 | May | 2025-07-15 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-07-22 | July | 7
DIAMOND | Tanvir | Pyramid | PYRAMID | PO00056315 | 44 | Replenishment | 13463 | 113 | Kuwait | Lamar Jewellery FZ-LLC | DIRECT | CONFIRMED | 2025-04-26 | April | 2025-05-06 | May | 2025-07-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-07-15 | July | 7
DIAMOND | Tanvir | Diana | GLAM | PO00056316 | 33 | Replenishment | 19700 | 153 | Bahrain | Lamar Jewellery FZ-LLC | DIRECT | HOLD | 2025-05-29 | May | 2025-06-09 | June | 2025-08-11 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-09-10 | September | 30
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056317 | 77 | Newness | 19809 | 182 | Saudi | Lamar Jewellery FZ-LLC | DIRECT | CONFIRMED | 2025-06-07 | June | 2025-06-17 | June | 2025-08-19 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-08-29 | August | 10
DIAMOND | Neha | GAIA | BRILLIANT | PO00056318 | 76 | Replenishment | 13102 | 102 | Kuwait | LOTUS JEWELS FZC | CONSIGNMENT | CONFIRMED | 2025-05-19 | May | 2025-05-28 | May | 2025-07-30 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-08-20 | August | 21
DIAMOND | Tanvir | Youth | PICK_ANY | PO00056319 | 68 | Newness | 13122 | 168 | Oman | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-07-26 | July | 2025-08-05 | August | 2025-10-07 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-11-19 | November | 43
FINE | Naju | Revolve Men | NO COLLECTION | PO00056320 | 41 | Replenishment | 14017 | 101 | Saudi | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-06-19 | June | 2025-06-30 | June | 2025-09-01 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-09-17 | September | 16
DIAMOND | Tanvir | Pyramid | PYRAMID | PO00056321 | 56 | Replenishment | 21487 | 183 | Saudi | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-07-06 | July | 2025-07-15 | July | 2025-09-16 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-10-28 | October | 42
FINE | Naju | Revolve Men | NO COLLECTION | PO00056322 | 58 | Replenishment | 19165 | 151 | Bahrain | RENAISSANCE JEWELLERY DMCC | DIRECT | CONFIRMED | 2025-04-21 | April | 2025-04-30 | April | 2025-07-02 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-07-25 | July | 23
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056323 | 34 | Newness | 21294 | 106 | Kuwait | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-03-06 | March | 2025-03-17 | March | 2025-05-19 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-05-25 | May | 6
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056324 | 36 | Replenishment | 20224 | 120 | UAE | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-05-08 | May | 2025-05-19 | May | 2025-07-21 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-08-23 | August | 33
DIAMOND | Tanvir | Youth | PICK_ANY | PO00056325 | 40 | Newness | 13925 | 119 | Qatar | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-03-31 | March | 2025-04-09 | April | 2025-06-11 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-07-19 | July | 38
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056326 | 39 | Replenishment | 18047 | 193 | Qatar | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-07-23 | July | 2025-08-01 | August | 2025-10-03 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-10-19 | October | 16
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056327 | 45 | Replenishment | 20665 | 103 | UAE | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-02-19 | February | 2025-02-28 | February | 2025-05-02 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-05-21 | May | 19
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056328 | 47 | Replenishment | 22870 | 142 | Bahrain | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-03-13 | March | 2025-03-24 | March | 2025-05-26 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-06-12 | June | 17
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056329 | 64 | Newness | 24746 | 129 | Saudi | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-06-09 | June | 2025-06-18 | June | 2025-08-20 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-10-02 | October | 43
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056330 | 47 | Replenishment | 21326 | 162 | Bahrain | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-03-03 | March | 2025-03-12 | March | 2025-05-14 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-07-03 | July | 50
DIAMOND | Harry | One Six Eight | Amara | PO00056331 | 59 | Replenishment | 16619 | 105 | UAE | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-07-25 | July | 2025-08-05 | August | 2025-10-07 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-11-26 | November | 50
FINE | Naju | Revolve Men | NO COLLECTION | PO00056332 | 80 | Newness | 16962 | 99 | UAE | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-03-09 | March | 2025-03-18 | March | 2025-05-20 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-05-26 | May | 6
DIAMOND | Harry | Illusion Round | Amara | PO00056333 | 46 | Newness | 14318 | 94 | Oman | Golden Star Exports Ltd | DIRECT | CONFIRMED | 2025-05-04 | May | 2025-05-13 | May | 2025-07-15 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-08-19 | August | 35
DIAMOND | Tanvir | Pyramid | PYRAMID | PO00056334 | 33 | Replenishment | 13434 | 94 | Saudi | Golden Star Exports Ltd | DIRECT | CONFIRMED | 2025-02-17 | February | 2025-02-26 | February | 2025-04-30 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-05-11 | May | 11
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056335 | 45 | Newness | 12143 | 138 | Saudi | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-02-04 | February | 2025-02-13 | February | 2025-04-17 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-05-27 | May | 40
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056336 | 57 | Replenishment | 12859 | 160 | Kuwait | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-04-04 | April | 2025-04-15 | April | 2025-06-17 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-07-29 | July | 42
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056337 | 39 | Newness | 21885 | 95 | Bahrain | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-03-09 | March | 2025-03-18 | March | 2025-05-20 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-06-26 | June | 37
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056338 | 55 | Newness | 16029 | 168 | Kuwait | RENAISSANCE JEWELLERY DMCC | DIRECT | NOT PLACED | 2025-08-18 | August | 2025-08-27 | August | 2025-10-29 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-11-21 | November | 23
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056339 | 35 | Newness | 16113 | 160 | UAE | RENAISSANCE JEWELLERY DMCC | DIRECT | CONFIRMED | 2025-08-08 | August | 2025-08-19 | August | 2025-10-21 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-11-17 | November | 27
FINE | Naju | Alif | ETERNAL | PO00056340 | 80 | Newness | 21310 | 159 | Saudi | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-05-28 | May | 2025-06-06 | June | 2025-08-08 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-08-19 | August | 11
DIAMOND | Harry | One Six Eight | Amara | PO00056341 | 38 | Replenishment | 22800 | 106 | Bahrain | LOTUS JEWELS FZC | DIRECT | HOLD | 2025-06-30 | June | 2025-07-09 | July | 2025-09-10 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-09-27 | September | 17
DIAMOND | Harry | Illusion Round | Amara | PO00056342 | 65 | Replenishment | 24002 | 191 | Qatar | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-07-24 | July | 2025-08-04 | August | 2025-10-06 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-11-12 | November | 37
DIAMOND | Harry | Illusion Round | Amara | PO00056343 | 39 | Replenishment | 19444 | 156 | Bahrain | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-02-13 | February | 2025-02-24 | February | 2025-04-28 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-05-05 | May | 7
FASHION | Nigora | OGL | GRANADA | PO00056344 | 76 | Replenishment | 15064 | 206 | Qatar | LOTUS JEWELS FZC | DIRECT | NOT PLACED | 2025-02-09 | February | 2025-02-18 | February | 2025-04-22 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-05-25 | May | 33
FASHION | Nigora | KIKU | CADEAU_SINGLE_CUT_P | PO00056345 | 57 | Replenishment | 24354 | 106 | Oman | RENAISSANCE JEWELLERY DMCC | DIRECT | NOT PLACED | 2025-06-05 | June | 2025-06-16 | June | 2025-08-18 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-10-03 | October | 46
DIAMOND | Harry | One Six Eight | Amara | PO00056346 | 75 | Newness | 19146 | 173 | Bahrain | LOTUS JEWELS FZC | DIRECT | CONFIRMED | 2025-02-27 | February | 2025-03-10 | March | 2025-05-12 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-06-24 | June | 43
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056347 | 48 | Newness | 14205 | 103 | Bahrain | Lamar Jewellery FZ-LLC | DIRECT | CONFIRMED | 2025-07-23 | July | 2025-08-01 | August | 2025-10-03 | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 27.27% | PO Created | 2025-10-10 | October | 7
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056348 | 49 | Replenishment | 15697 | 169 | Saudi | Golden Star Exports Ltd | DIRECT | HOLD | 2025-08-02 | August | 2025-08-12 | August | 2025-10-14 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | 54.55% | In Production | 2025-11-10 | November | 27
FINE | Naju | Stella Doro | NO COLLECTION | PO00056349 | 39 | Newness | 20280 | 208 | Bahrain | Golden Star Exports Ltd | DIRECT | HOLD | 2025-06-06 | June | 2025-06-17 | June | 2025-08-19 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | 100% | Shipment Complete | 2025-09-09 | September | 21
FASHION | Nigora | OGL | GRANADA | PO00056350 | 42 | Replenishment | 23323 | 115 | Kuwait | Golden Star Exports Ltd | DIRECT | NOT PLACED | 2025-07-22 | July | 2025-07-31 | July | 2025-10-02 | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 45.45% | Order Confirmed | 2025-10-25 | October | 23
GOLD | Reddy | Anmol 21K | Floret_21 | PO00056351 | 71 | Replenishment | 20389 | 160 | Qatar | RENAISSANCE JEWELLERY DMCC | DIRECT | NOT PLACED | 2025-07-30 | July | 2025-08-08 | August | 2025-10-10 | TRUE | TRUE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | FALSE | 18.18% | Order Approved | 2025-10-19 | October | 9
GOLD | Reddy | Nakshatrah | NO COLLECTION | PO00056352 | 60 | Newness | 22096 | 208 | UAE | Lamar Jewellery FZ-LLC | DIRECT | NOT PLACED | 2025-02-24 | February | 2025-03-05 | March | 2025-05-07 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | FALSE | 81.82% | QC Checks | 2025-05-24 | May | 17
FINE | Naju | Alif | ETERNAL | PO00056353 | 66 | Replenishment | 20224 | 205 | Kuwait | Golden Star Exports Ltd | DIRECT | HOLD | 2025-04-15 | April | 2025-04-24 | April | 2025-06-26 | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE | 90.91% | Delivered to DIAMOND DC | 2025-07-21 | July | 25
Formulas:
PO Creation Date = WORKDAY([OTB Creation Date],7)
ETA = WORKDAY([PO Creation Date],45)
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.
This shape represents a table slicer. Table slicers are not supported in this version of Excel. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2007 or earlier, the slicer can't be used.

## Dashboard
PROCUREMENT AND SHIPMENT TRACKER
| Total OTB Value | Total OTB Qty | ✅ % of POs Confirmed | 🚚 % of POs In Transit | 📦 % Delivered to DC | 🧪 % Passed QC | 🔁 % Orders Completed
| 1831418 | 14897 | 71.43% | 46.94% | 29.59% | 46.94% | 12.24%
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.